## Sheet1
Decentralized Capital Budget Programme -2017 As at 30-10-2018
Name of DS Division: |  | Kalmunai Tamil |  |  | Name of Programme: |  |  | DCB
SL No | Name of the project | Allocation in MN | Source of fund | Date of Tecder / Quotation called | Date of tender Awarted | Physical Progress |  |  |  |  | Expenditure in Mn | Remarks
[6 empty] | Not started | 25% | 50% | 75% | 100%
1 | Supplying furnitures and school goods to Thirumakal Aranery School | 0.05 | DCB | 28.06.2018 | 10.08.2018 |  |  |  |  | 1 | 0.05
2 | Purchasing of hurts & Chairs women socity pandiruppu | 0.2 | DCB | 31.07.2018 | 27.09.2018 |  |  |  |  | 1 | 0.199
3 | Purchasing of Furniture and play equipment pre school childern pre-school | 0.04 | DCB | Ammentment |  | 1 | [5 empty] | Ammended
4 | Supplying photocopier& multimedia Fatima college-Kalmunai | 0.1 | DCB | 31.07.2018 | 11.10.2018 |  |  |  |  | 1 | 0.099
5 | Construction of vishnu kovil -Pandiruppu | 0.1 | DCB | 31.07.2018 | 27.09.2018 |  |  |  |  | 1 | 0.084
6 | Supplying photocopy Mechine to Vipulananda vidyalaya | 0.07 | DCB | Ammentment |  | 1 | [5 empty] | Ammended
| Total | 0.56 |  |  |  | 2 |  |  |  | 4 | 0.432