## Sheet1
Progres of ONUR Development Works As at 30-10-2018
Name of DS Division: |  | Kalmunai Tamil |  |  | Name of Programme: |  |  | ONUR
SL No | Name of the project | Allocation in MN | Source of fund | Date of Tecder / Quotation called | Date of tender Awarted | Physical Progress |  |  |  |  | Expenditure in Mn | Remarks
[6 empty] | Not started | 25% | 50% | 75% | 100%
1 | Providing of Livelihood Assistance for Fisherman Equipments (Fishing net&Tools) | 0.2 | ONUR | 10.07.2018 | 10.09.2018 |  |  |  |  | 1 | 0.2
2 | Providing of Home Garden Euipments (Water Pums, Course pipes) | 0.2 | ONUR | 10.07.2018 | 10.09.2018 |  |  |  |  | 1 | 0.2
3 | Providing Handloom Machinery | 0.5 | ONUR | 10.07.2018 | 10.09.2018 |  |  |  | 1
4 | Providing Handloom Machinery | 0.5 | ONUR | 10.07.2018 | 10.09.2018 |  |  |  | 1
| Total | 1.4 | [6 empty] | 2 | 2 | 0.4