## Sheet1
Progres of REESP Development Works As at 30-10-2018
Name of DS Division: |  | Kalmunai Tamil |  |  | Name of Programme: |  |  | REESP
SL No | Name of the project | Allocation in MN | Source of fund | Date of Tecder / Quotation called | Date of tender Awarted | Physical Progress |  |  |  |  | Expenditure in Mn | Remarks
[6 empty] | Not started | 25% | 50% | 75% | 100%
1 | Renovation of Sri Muththumari Amman Kovil | 0.5 | REESP | 13.10.2018 | 29.10.2018 |  | 1
2 | Renovation of Sri Nagathampiran Alyam | 2 | REESP | 13.10.2018 | 29.10.2018 |  | 1
3 | Construction of Drainage and Road at Kamachi Amman Kovil Road | 2 | REESP | 13.10.2018 | 29.10.2018 |  | 1
4 | Construction of Drainage and Road at Chairman Road Cross | 2 | REESP | 13.10.2018 | 29.10.2018 |  | 1
5 | Construction of Concrete Road at behind Pillayar Kovil 3rd cross road, Pandiruppu | 0.4 | REESP | 13.10.2018 | 29.10.2018 |  | 1
6 | Construction of Concrete Road at behind Pillayar Kovil 01st cross road, Pandiruppu | 0.4 | REESP | 13.10.2018 | 29.10.2018 |  | 1
7 | Construction of Internal Lighting at cemetery, Pandiruppu. | 1 | REESP | 18.10.2018 |  | 1
8 | Construction of Road and Drainage at cemetery, Pandiruppu. | 1.8 | REESP | 18.10.2018 |  | 1
| Total | 10.1 |  |  |  | 2 | 6