## Sheet1
Progres of Religious Places Development Works As at 30-10-2018
Name of DS Division: |  | Kalmunai Tamil |  |  | Name of Programme: |  |  | Religious Places
SL No | Name of the project | Allocation in MN | Source of fund | Date of Tecder / Quotation called | Date of tender Awarted | Physical Progress |  |  |  |  | Expenditure in Mn | Remarks
[6 empty] | Not started | 25% | 50% | 75% | 100%
1 | Renovation of Manikkapillaiyar Temple, Thuraivanthiyamadu | 0.1 | Ministry of National Policies and Economic Affairs | 17.07.2018 | 11.09.2018 |  |  |  | 1
2 | Renovation of Pandiruppu Sri Sivan Alayam, Beach Road , Pandiruppu - 01, Kalmunai. | 0.1 | Ministry of National Policies and Economic Affairs | 17.07.2018 | 11.09.2018 |  |  |  |  | 1 | 0.085
3 | Renovation Of Kurunthaiyadi Sri Selvavinayagar Temple, Kurunthaiyadi, Kalmunai T.D | 0.1 | Ministry of National Policies and Economic Affairs | 17.07.2019 | 11.09.2018 |  |  |  |  | 1 | 0.085
4 | Renovation of Sri Maha Vishnu Temple, Natpadimunai, Kalmunai | 0.1 | Ministry of National Policies and Economic Affairs | 17.07.2019 | 11.09.2018 |  |  |  |  | 1 | 0.085
| Total | 0.4 | [6 empty] | 1 | 3 | 0.255